## verification_plan
ID | Feature area | Verification item | testing pattern name | command.txt task name | suite | covered by | testing pattern description | spec section | constraint items | random or directed | mode/speed | instance | checkers active | notes
A. Register Access (APB)
CMD-001 | Register Access (APB) | External register read/write sweep (no USB traffic) | extreg_rw | pat_extreg_rw | infra | NOT COVERED | APB external-register read/write sweep, GLOBAL_INIT + REG_usbextreg_TSET(8'hff,8'h0); no runtime args, fixed sequence. | TBD-spec |  | directed | N/A (no USB traffic; APB-only) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/extreg_rw.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH per command_inventory.csv CMD-001). Real BFM-port task pat_extreg_rw exists at D:/DV/Task/USB/uvm/tb/patterns/infra/extreg_rw.txt and IS registered in pattern_list.txt (runtime-selectable via PATTERN=extreg_rw) -- but that port itself notes a real gap: 'Left commented: the task lives in usbextreg_less.tb.txt ... not in the delivery' (REG_usbextreg_TSET sweep not reproduced). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_extreg_rw, registered via PATTERN=extreg_rw) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
B. USB2 Bulk Transfer
CMD-002 | USB2 Bulk Transfer | USB2 HS Bulk-IN bring-up and transfer | usb2_bulkin | pat_usb2_bulkin | transfer | NOT COVERED | Fixed HS bulk-in bring-up + transfer (no runtime args in file). | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_bulkin.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_bulkin exists and is registered (PATTERN=usb2_bulkin). command_inventory.csv's own VIP_SEQUENCE column cites usb_device_enumeration_vseq (examples/generated_usb_real_evidence_v11+, tb/seq/usb_base_vseq.sv) as 'partial overlap only: shares SET_ADDRESS/enum bring-up region ... NOT yet a full conversion' -- that sequence covers only the shared enumeration preamble, not this pattern's own bulk-transfer data-integrity checking, and is not wired to this pattern's own BFM-port task. No scoreboard check backs the bulk-in data path itself. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_bulkin, registered via PATTERN=usb2_bulkin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-003 | USB2 Bulk Transfer | USB2 HS Bulk-OUT bring-up and transfer | usb2_bulkout | pat_usb2_bulkout | transfer | NOT COVERED | Fixed HS bulk-out bring-up + transfer. | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_bulkout.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_bulkout exists and is registered (PATTERN=usb2_bulkout). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_bulkout, registered via PATTERN=usb2_bulkout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
C. USB2 Enumeration / Connect
CMD-004 | USB2 Enumeration / Connect | USB2 device connect/enumeration bring-up | usb2_con | pat_usb2_con | enumeration | NOT COVERED | Device connect/enumeration bring-up only (no transfer). | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_con.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=MEDIUM). Real BFM-port task pat_usb2_con exists and is registered (PATTERN=usb2_con). command_inventory.csv's own VIP_SEQUENCE column cites usb_device_enumeration_vseq (examples/generated_usb_real_evidence_v11+, tb/seq/usb_base_vseq.sv) as the 'closest existing overlap -- round-10 output models the same standard enumeration handshake independently from VIP/spec evidence, not from this file' -- real functional overlap (GET_DESCRIPTOR/SET_ADDRESS/SET_CONFIGURATION), zero provenance link to THIS pattern's own pat_usb2_con BFM-port task, and it is not wired as that task's checker. The 2 real scoreboard checks generated this session (SB_EP_EPTYPE_DUT_VIP_CONFIG_AGREEMENT, SB_EP_MPS_DUT_VIP_CONFIG_AGREEMENT in examples/generated_usb_real_evidence_v12/tb/env/usb_scoreboard.sv) check endpoint-config agreement, not this pattern's enumeration handshake itself. Not credited as covered/PARTIAL per this round's honesty rule. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_con, registered via PATTERN=usb2_con) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
D. USB2 Interrupt Transfer
CMD-005 | USB2 Interrupt Transfer | USB2 HS Interrupt-IN transfer | usb2_intin | pat_usb2_intin | transfer | NOT COVERED | HS interrupt-in (adapted from USB2_bulkin.txt per its own header). | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_interruptin.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_intin exists and is registered (PATTERN=usb2_intin). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_intin, registered via PATTERN=usb2_intin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-006 | USB2 Interrupt Transfer | USB2 HS Interrupt-IN transfer on EP1 | usb2_intin_ep1 | pat_usb2_intin_ep1 | transfer | NOT COVERED | HS interrupt-in on EP1 (adapted from USB2_interruptin.txt). | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_interruptin_ep1.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_intin_ep1 exists and is registered (PATTERN=usb2_intin_ep1). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_intin_ep1, registered via PATTERN=usb2_intin_ep1) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-007 | USB2 Interrupt Transfer | USB2 HS Interrupt-IN transfer, bInterval=3 variant | usb2_intin_int3 | pat_usb2_intin_int3 | transfer | NOT COVERED | HS interrupt-in bInterval=3 variant (adapted from USB2_bulkin.txt). | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_interruptin_intervel3.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_intin_int3 exists and is registered (PATTERN=usb2_intin_int3). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_intin_int3, registered via PATTERN=usb2_intin_int3) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-008 | USB2 Interrupt Transfer | USB2 HS Interrupt-OUT transfer | usb2_intout | pat_usb2_intout | transfer | NOT COVERED | HS interrupt-out (adapted from USB2_bulkout.txt). | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_interruptout.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_intout exists and is registered (PATTERN=usb2_intout). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_intout, registered via PATTERN=usb2_intout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
E. USB2 Isochronous Transfer
CMD-009 | USB2 Isochronous Transfer | USB2 HS Isochronous-IN transfer | usb2_isocin | pat_usb2_isocin | transfer | NOT COVERED | HS isochronous-in. | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_isochin.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_isocin exists and is registered (PATTERN=usb2_isocin). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_isocin, registered via PATTERN=usb2_isocin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-010 | USB2 Isochronous Transfer | USB2 HS Isochronous-IN transfer, bInterval=3 variant | usb2_isocin_int3 | pat_usb2_isocin_int3 | transfer | NOT COVERED | HS isochronous-in bInterval=3 variant. | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_isochin_intervel3.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_isocin_int3 exists and is registered (PATTERN=usb2_isocin_int3). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_isocin_int3, registered via PATTERN=usb2_isocin_int3) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-011 | USB2 Isochronous Transfer | USB2 HS Isochronous-IN transfer, transfer-not-ready case | usb2_isocin_xnr | pat_usb2_isocin_xnr | transfer | NOT COVERED | HS isochronous-in transfer-not-ready case (adapted from USB2_isochin.txt). | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_isochin_xfernotready.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_isocin_xnr exists and is registered (PATTERN=usb2_isocin_xnr). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_isocin_xnr, registered via PATTERN=usb2_isocin_xnr) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-012 | USB2 Isochronous Transfer | USB2 HS Isochronous-OUT transfer | usb2_isocout | pat_usb2_isocout | transfer | NOT COVERED | HS isochronous-out (adapted from USB2_bulkout.txt). | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_isochout.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_isocout exists and is registered (PATTERN=usb2_isocout). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_isocout, registered via PATTERN=usb2_isocout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
F. USB2 Power Management
CMD-013 | USB2 Power Management | USB2 host suspend/resume | usb2_susres | pat_usb2_susres | power | NOT COVERED | USB2 host suspend/resume. | TBD-spec |  | directed | USB2.0 HS (SPEED0=usb20) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB2_susres.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb2_susres exists and is registered (PATTERN=usb2_susres). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb2_susres, registered via PATTERN=usb2_susres) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
G. USB3 Power Management
CMD-014 | USB3 Power Management | USB3 host suspend/resume | usb3_susres | pat_usb3_susres | power | NOT COVERED | USB3 host suspend/resume (file header says USB2 but filename/content targets USB3 -- flagged in command_inventory.csv, not silently corrected here either). | TBD-spec |  | directed | USB3 (SPEED0=gen1¦gen2; original file's own header claims USB2 -- unresolved header/content mismatch, CONFIDENCE=MEDIUM in command_inventory.csv) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB3_susres.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=MEDIUM -- header/content protocol mismatch flagged, unresolved). Real BFM-port task pat_usb3_susres exists and is registered (PATTERN=usb3_susres). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb3_susres, registered via PATTERN=usb3_susres) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
H. USB3.1 SuperSpeed(+) Enumeration / Connect
CMD-015 | USB3.1 SuperSpeed(+) Enumeration / Connect | USB3.1 SuperSpeed(+) device connect/enumeration bring-up | usb31_sscon | pat_usb31_sscon | link | NOT COVERED | SuperSpeed(+) device connect/enumeration bring-up only. | TBD-spec |  | directed | USB3.1 SuperSpeed(+) (SPEED0=gen1¦gen2) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB31_SScon.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb31_sscon exists and is registered (PATTERN=usb31_sscon). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb31_sscon, registered via PATTERN=usb31_sscon) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-019 | USB3.1 SuperSpeed(+) Enumeration / Connect | USB3.1 SuperSpeed(+) connect, second variant file | usb31_sspcon | pat_usb31_sspcon | link | NOT COVERED | SuperSpeed(+) connect -- second file with same PROTOCOL/COMMAND as CMD-015; real content diff between USB31_SScon.txt and USB31_SSPcon.txt not yet compared (command_inventory.csv CONFIDENCE=LOW on this row specifically). | TBD-spec |  | directed | USB3.1 SuperSpeed(+) (SPEED0=gen1¦gen2) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB31_SSPcon.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=LOW -- content diff vs CMD-015's USB31_SScon.txt not yet compared). Real BFM-port task pat_usb31_sspcon exists and is registered (PATTERN=usb31_sspcon) -- a DISTINCT real registered pattern from CMD-015's pat_usb31_sscon (confirmed both present, separately, in pattern_list.txt). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb31_sspcon, registered via PATTERN=usb31_sspcon) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
I. USB3.1 SuperSpeed(+) Bulk Transfer
CMD-016 | USB3.1 SuperSpeed(+) Bulk Transfer | USB3.1 SuperSpeed(+) Bulk-IN bring-up and transfer | usb31_sspbulkin | pat_usb31_sspbulkin | transfer | NOT COVERED | SuperSpeed(+) bulk-in bring-up + transfer. | TBD-spec |  | directed | USB3.1 SuperSpeed(+) (SPEED0=gen1¦gen2) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB31_SSPbulkin.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb31_sspbulkin exists and is registered (PATTERN=usb31_sspbulkin). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb31_sspbulkin, registered via PATTERN=usb31_sspbulkin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-017 | USB3.1 SuperSpeed(+) Bulk Transfer | USB3.1 SuperSpeed(+) Bulk-OUT bring-up and transfer | usb31_sspbulkout | pat_usb31_sspbulkout | transfer | NOT COVERED | SuperSpeed(+) bulk-out bring-up + transfer. | TBD-spec |  | directed | USB3.1 SuperSpeed(+) (SPEED0=gen1¦gen2) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB31_SSPbulkout.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb31_sspbulkout exists and is registered (PATTERN=usb31_sspbulkout). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb31_sspbulkout, registered via PATTERN=usb31_sspbulkout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-018 | USB3.1 SuperSpeed(+) Bulk Transfer | USB3.1 SuperSpeed(+) Bulk-OUT, DE-authored teaching copy (not a distinct scenario) |  |  | transfer | N/A | Same test content as USB31_SSPbulkout.txt with extra inline explanatory comments (DE-authored teaching copy). | TBD-spec |  | directed | N/A -- not a distinct runtime pattern | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB31_SSPbulkout_explain.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=MEDIUM, per command_inventory.csv: 'same as USB31_SSPbulkout.txt with extra inline explanatory comments -- not a distinct test scenario'). Confirmed this session: no BFM-port counterpart exists for it -- absent from D:/DV/Task/USB/uvm/tb/patterns/pattern_list.txt and from dv_uvm_pattern_pool.svh's include list (unlike every other row in this vPlan, which do have one). Marked N/A rather than NOT COVERED: it is not a distinct verification requirement, it is CMD-017's own content with added comments.
J. USB3.1 SuperSpeed(+) Interrupt Transfer
CMD-020 | USB3.1 SuperSpeed(+) Interrupt Transfer | USB3.1 SuperSpeed(+) Interrupt-IN transfer | usb31_sspintin | pat_usb31_sspintin | transfer | NOT COVERED | SuperSpeed(+) interrupt-in (adapted from USB31_SSPbulkin.txt). | TBD-spec |  | directed | USB3.1 SuperSpeed(+) (SPEED0=gen1¦gen2) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB31_SSPinterruptin.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb31_sspintin exists and is registered (PATTERN=usb31_sspintin). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb31_sspintin, registered via PATTERN=usb31_sspintin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-021 | USB3.1 SuperSpeed(+) Interrupt Transfer | USB3.1 SuperSpeed(+) Interrupt-OUT transfer | usb31_sspintout | pat_usb31_sspintout | transfer | NOT COVERED | SuperSpeed(+) interrupt-out (adapted from USB31_SSPbulkout.txt). | TBD-spec |  | directed | USB3.1 SuperSpeed(+) (SPEED0=gen1¦gen2) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB31_SSPinterruptout.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb31_sspintout exists and is registered (PATTERN=usb31_sspintout). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb31_sspintout, registered via PATTERN=usb31_sspintout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
K. USB3.1 SuperSpeed(+) Isochronous Transfer
CMD-022 | USB3.1 SuperSpeed(+) Isochronous Transfer | USB3.1 SuperSpeed(+) Isochronous-IN transfer | usb31_sspisocin | pat_usb31_sspisocin | transfer | NOT COVERED | SuperSpeed(+) isochronous-in (adapted from USB31_SSPbulkin.txt). | TBD-spec |  | directed | USB3.1 SuperSpeed(+) (SPEED0=gen1¦gen2) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB31_SSPisochin.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb31_sspisocin exists and is registered (PATTERN=usb31_sspisocin). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb31_sspisocin, registered via PATTERN=usb31_sspisocin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-023 | USB3.1 SuperSpeed(+) Isochronous Transfer | USB3.1 SuperSpeed(+) Isochronous-IN transfer, transfer-not-ready case | usb31_sspisocin_xnr | pat_usb31_sspisocin_xnr | transfer | NOT COVERED | SuperSpeed(+) isochronous-in transfer-not-ready case (adapted from USB31_SSPisochin.txt). | TBD-spec |  | directed | USB3.1 SuperSpeed(+) (SPEED0=gen1¦gen2) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB31_SSPisochin_xfernotready.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb31_sspisocin_xnr exists and is registered (PATTERN=usb31_sspisocin_xnr). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb31_sspisocin_xnr, registered via PATTERN=usb31_sspisocin_xnr) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))
CMD-024 | USB3.1 SuperSpeed(+) Isochronous Transfer | USB3.1 SuperSpeed(+) Isochronous-OUT transfer | usb31_sspisocout | pat_usb31_sspisocout | transfer | NOT COVERED | SuperSpeed(+) isochronous-out (adapted from USB31_SSPbulkout.txt). | TBD-spec |  | directed | USB3.1 SuperSpeed(+) (SPEED0=gen1¦gen2) | block.branch_a0 |  | Original DE file: D:/DV/Task/USB/patterns/USB31_SSPisochout.txt (STATUS=DE_ORIGINAL_UNCONVERTED, CONFIDENCE=HIGH). Real BFM-port task pat_usb31_sspisocout exists and is registered (PATTERN=usb31_sspisocout). No generated UVM sequence/scoreboard content in examples/generated_usb_real_evidence_v9-v12 touches this pattern. (blocked_on=EFFORT; blocked_reason=Real BFM-port task (pat_usb31_sspisocout, registered via PATTERN=usb31_sspisocout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.))

## coverage_summary
Table A — Counts by covered-by state
State | Count | % of total | Credited toward coverage goal
covered | 0 | 0 | Yes
PARTIAL | 0 | 0 | No
NOT COVERED | 23 | 95.83 | No
N/A | 1 | 4.17 | Yes
DEFERRED | 0 | 0 | No
TOTAL | 24
Coverage % | 4.17
Table B — Gaps ranked
Rank | ID | Feature area | Verification item | covered by | blocked on | why it is next
1 | CMD-001 | Register Access (APB) | External register read/write sweep (no USB traffic) | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_extreg_rw, registered via PATTERN=extreg_rw) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
2 | CMD-002 | USB2 Bulk Transfer | USB2 HS Bulk-IN bring-up and transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_bulkin, registered via PATTERN=usb2_bulkin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
3 | CMD-003 | USB2 Bulk Transfer | USB2 HS Bulk-OUT bring-up and transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_bulkout, registered via PATTERN=usb2_bulkout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
4 | CMD-004 | USB2 Enumeration / Connect | USB2 device connect/enumeration bring-up | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_con, registered via PATTERN=usb2_con) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
5 | CMD-005 | USB2 Interrupt Transfer | USB2 HS Interrupt-IN transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_intin, registered via PATTERN=usb2_intin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
6 | CMD-006 | USB2 Interrupt Transfer | USB2 HS Interrupt-IN transfer on EP1 | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_intin_ep1, registered via PATTERN=usb2_intin_ep1) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
7 | CMD-007 | USB2 Interrupt Transfer | USB2 HS Interrupt-IN transfer, bInterval=3 variant | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_intin_int3, registered via PATTERN=usb2_intin_int3) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
8 | CMD-008 | USB2 Interrupt Transfer | USB2 HS Interrupt-OUT transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_intout, registered via PATTERN=usb2_intout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
9 | CMD-009 | USB2 Isochronous Transfer | USB2 HS Isochronous-IN transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_isocin, registered via PATTERN=usb2_isocin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
10 | CMD-010 | USB2 Isochronous Transfer | USB2 HS Isochronous-IN transfer, bInterval=3 variant | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_isocin_int3, registered via PATTERN=usb2_isocin_int3) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
11 | CMD-011 | USB2 Isochronous Transfer | USB2 HS Isochronous-IN transfer, transfer-not-ready case | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_isocin_xnr, registered via PATTERN=usb2_isocin_xnr) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
12 | CMD-012 | USB2 Isochronous Transfer | USB2 HS Isochronous-OUT transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_isocout, registered via PATTERN=usb2_isocout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
13 | CMD-013 | USB2 Power Management | USB2 host suspend/resume | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb2_susres, registered via PATTERN=usb2_susres) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
14 | CMD-014 | USB3 Power Management | USB3 host suspend/resume | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb3_susres, registered via PATTERN=usb3_susres) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
15 | CMD-015 | USB3.1 SuperSpeed(+) Enumeration / Connect | USB3.1 SuperSpeed(+) device connect/enumeration bring-up | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb31_sscon, registered via PATTERN=usb31_sscon) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
16 | CMD-019 | USB3.1 SuperSpeed(+) Enumeration / Connect | USB3.1 SuperSpeed(+) connect, second variant file | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb31_sspcon, registered via PATTERN=usb31_sspcon) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
17 | CMD-016 | USB3.1 SuperSpeed(+) Bulk Transfer | USB3.1 SuperSpeed(+) Bulk-IN bring-up and transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb31_sspbulkin, registered via PATTERN=usb31_sspbulkin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
18 | CMD-017 | USB3.1 SuperSpeed(+) Bulk Transfer | USB3.1 SuperSpeed(+) Bulk-OUT bring-up and transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb31_sspbulkout, registered via PATTERN=usb31_sspbulkout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
19 | CMD-020 | USB3.1 SuperSpeed(+) Interrupt Transfer | USB3.1 SuperSpeed(+) Interrupt-IN transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb31_sspintin, registered via PATTERN=usb31_sspintin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
20 | CMD-021 | USB3.1 SuperSpeed(+) Interrupt Transfer | USB3.1 SuperSpeed(+) Interrupt-OUT transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb31_sspintout, registered via PATTERN=usb31_sspintout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
21 | CMD-022 | USB3.1 SuperSpeed(+) Isochronous Transfer | USB3.1 SuperSpeed(+) Isochronous-IN transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb31_sspisocin, registered via PATTERN=usb31_sspisocin) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
22 | CMD-023 | USB3.1 SuperSpeed(+) Isochronous Transfer | USB3.1 SuperSpeed(+) Isochronous-IN transfer, transfer-not-ready case | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb31_sspisocin_xnr, registered via PATTERN=usb31_sspisocin_xnr) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
23 | CMD-024 | USB3.1 SuperSpeed(+) Isochronous Transfer | USB3.1 SuperSpeed(+) Isochronous-OUT transfer | NOT COVERED | EFFORT | NOT COVERED, blocked on EFFORT — Real BFM-port task (pat_usb31_sspisocout, registered via PATTERN=usb31_sspisocout) exists and is runtime-selectable, but no UVM-native VIP-sequence/scoreboard-backed verification content has been generated for it yet -- needs conversion effort. (examples/generated_usb_real_evidence_v9-v12 this session only produced usb_device_enumeration_vseq + 2 endpoint-config scoreboard checks, neither of which back this specific pattern's own task.)
Table C — Deferred (visible, not ranked)
ID | Feature area | Verification item | notes